## Sheet1
s.no | Module name | Overall Status | UI | Seed Data Setup | Api | Business Logic in Percentage | Database Tables and Design Done | Integration Api and Database | Action Pending
1 | Project Details | 70% | done | na | Not Started | 90% | Done | Not Started | As per Good UI Standards , need to be changed
2 | Standard Data (Seed Data) |  | na | Done | Not Started | 100% | Done | Not Started | Seed Data scripts need to be added to db project
3 | Inputs and Layouts |  | done | Done | Not Started | 90% | Done | Not Started | As per Good UI Standards , need to be changed
4 | Design Calculations |  | done | na | Not Started | 90% | Done | Not Started | 85% Business logic is done in console application
5 | Report | Not Started | Not Started |  | Not Started | Not Started | Not Started | Not Started | Requirement Gathering from Client is pending on this